## Comparison
PROPOSAL REQUEST FORM
[5 empty] | General Contractor |  | External Cost | Total
| CSI Code |  |  | Category | Material | Labor
SOFT COSTS
| 00 | 11 | 20 | Architect |  |  |  | 0
| 00 | 12 | 10 | Environmental Consultant |  |  |  | 0
| 00 | 13 | 30 | Permits and Fees |  | 0 |  | 0
HARD COSTS
| 01 | 01 | 40 | Final Cleaning | 50 | 250 |  | 300
| 02 | 41 | 05 | Demolition | 400 | 1200 | H | 1600
| 02 | 41 | 10 | Hauling | 600 | 600 | H | 1200
| 02 | 81 | 05 | Abatement |  |  |  | 0
| 06 | 11 | 05 | Rough Carpentry/Framing | 2700 | 6200 | H | 8900
| 06 | 41 | 05 | Cabinets |  | 1800 | H | 1800
| 06 | 61 | 05 | Countertop / Backsplash |  | 2600 |  | 2600
| 06 | 46 | 10 | Trim / Baseboard / Molding / Shelving | 2350 | 6400 | H | 8750
| 07 | 20 | 05 | Insulation | 325 | 600 | H | 925
| 08 | 11 | 05 | Doors & Hardware x 2 - doors | 620 | 1600 | H | 2220
| 08 | 50 | 10 | Window Repair | 0 | 0 | H | 0
| 09 | 29 | 05 | Drywall | 1500 | 9000 |  | 10500
| 09 | 30 | 05 | Tile |  | 3500 |  | 3500
| 09 | 64 | 05 | Wood Flooring (New) |  | 0 |  | 0
| 09 | 01 | 60 | Floor Patch / Refinish Existing | 410 | 3500 |  | 3910
| 09 | 91 | 05 | Painting (Interior) | 510 | 5200 |  | 5710
| 10 | 25 | 05 | Bath Accessories |  | 450 | H | 450
| 11 | 31 | 05 | Appliances |  | 250 | H | 250
| 12 | 20 | 05 | Window Blinds | 466 | 800 | H | 1266
| 22 | 10 | 05 | Rough Plumbing | 1800 | 8400 |  | 10200
| 22 | 10 | 10 | Tub Replacement or Glazing | 0 | 0 | H | 0
| 22 | 42 | 05 | Finish Plumbing Fixtures/Trim |  | 450 |  | 450
| 23 | 31 | 20 | Heating System |  |  | H | 0
| 26 | 27 | 05 | Rough Electrical | 1600 | 8500 |  | 10100
| 26 | 50 | 05 | Finish Electrical Fixtures / Trim |  | 450 |  | 450
| 28 | 23 | 05 | Low Voltage Systems (Fire/Security/Cable) | 65 | 300 | H | 365
| 60 | 10 | 15 | Contractor's Fee / Profit & Overhead | 250 | 250 | H | 500
| 90 | 20 | 15 | Construction Management Fee |  |  | H | 0
Subtotal GC |  |  |  |  | 11646 | 53100 |  | 75946
Subtotal External Cost | [6 empty] | 0 | 0
TOTAL |  |  |  |  | 11646 | 53100 | 0 | 64746
[5 empty] | Materials | Wages
|  |  |  | In house budget of: | 7776 | 20450
Budget Report:
|  |  |  | Wages | 20450
|  |  |  | Materials | 7776
|  |  |  | Granite Fabr. | 2600
|  |  |  | (S)Tile | 3500
|  |  |  | (S)Plumbing | 10650
|  |  |  | (S)Painting | 5710
|  |  |  | (S)Flooring | 3910
|  |  |  | (S)Electrical | 10550
|  |  |  | (S)Drywall | 10500
|  |  |  | (S)Cleaning | 300
|  |  |  | ____ | 75946

## Cost 3.11.2022
4:26 PM
2022-03-11
Type | Account |  | Clr | Amount | Balance
Check | Wages | 1798.01 |  | 1798.01 | 1798.01
Check | Rent | 67.93 |  | 67.93 | 1865.94
Check | Transportation | 30 |  | 30 | 1895.94
Check | Permit Fee | 1958.02 |  | 1958.02 | 3853.96
Check | Plumbing | 5000 |  | 5000 | 8853.96
Check | Health Plan Insurance | 197.35 |  | 197.35 | 9051.31
Check | Plumbing | 7650 |  | 7650 | 16701.31
Check | Wages | 2396.32 |  | 2396.32 | 19097.63
Check | Lumber or plie Wood Material | 166.25 |  | 166.25 | 19263.88
Check | Materials | 138.7 |  | 138.7 | 19402.58
Check | Parking | 50 |  | 50 | 19452.58
Check | Gas | 213.25 |  | 213.25 | 19665.83
Check | Parking | 13.72 |  | 13.72 | 19679.55
Check | Payroll Processing Fees | 20 |  | 20 | 19699.55
Check | Rent | 48.49 |  | 48.49 | 19748.04
Check | Wages | 2367.12 |  | 2367.12 | 22115.16
Check | Health Plan Insurance | 30 |  | 30 | 22145.16
Check | Work Comp | 90.51 |  | 90.51 | 22235.67
Check | Health Plan Insurance | 140.71 |  | 140.71 | 22376.38
Check | Repairs & Maintenance | 331.3 |  | 331.3 | 22707.68
Check | Gas | 50 |  | 50 | 22757.68
Check | Parking | 50 |  | 50 | 22807.68
Check | Transportation | 30 |  | 30 | 22837.68
Check | Drywall | 2000 |  | 2000 | 24837.68
Check | Wages | 1404.92 |  | 1404.92 | 26242.6
Check | Gas | 149.56 |  | 149.56 | 26392.16
Check | Repairs & Maintenance | 79.11 |  | 79.11 | 26471.27
Check | Materials | 55.2 |  | 55.2 | 26526.47
Check | Work Comp | 53.94 |  | 53.94 | 26580.41
Check | Payroll Processing Fees | 15 |  | 15 | 26595.41
Check | Transportation | 30 |  | 30 | 26625.41
Check | Materials | 351.77 |  | 351.77 | 26977.18
Check | Health Plan Insurance | 15 |  | 15 | 26992.18
Check | Electrical | 6000 |  | 6000 | 32992.18
Check | Payroll Expenses MRA | 208.12 |  | 208.12 | 33200.3
Check | Rent | 150.68 |  | 150.68 | 33350.98
Check | Drywall | 5500 |  | 5500 | 38850.98
Check | Materials | 217.86 |  | 217.86 | 39068.84
Check | Health Insurance | 437.48 |  | 437.48 | 39506.32
Check | Wages | 3125.44 |  | 3125.44 | 42631.76
Check | Flooring | 3200 |  | 3200 | 45831.76
Check | General Liability Insurance | 146.16 |  | 146.16 | 45977.92
Check | Materials | 50 |  | 50 | 46027.92
Check | Tiling | 2500 |  | 2500 | 48527.92
Check | Wages | 6659.58 |  | 6659.58 | 55187.5
Check | Repairs & Maintenance | 573.18 |  | 573.18 | 55760.68
Check | Gas | 389.44 |  | 389.44 | 56150.12
Check | Parking | 10 |  | 10 | 56160.12
Check | Payroll Processing Fees | 27 |  | 27 | 56187.12
Check | Dues and Subscriptions | 20 |  | 20 | 56207.12
Check | Work Comp | 131.87 |  | 131.87 | 56338.99
Check | Lumber or plie Wood Material | 1936.77 |  | 1936.77 | 58275.76
Check | Automobile Expense | 484.35 |  | 484.35 | 58760.11
Check | Gas | 40 |  | 40 | 58800.11
Check | Parking | 15 |  | 15 | 58815.11
Check | Materials | 1201.59 |  | 1201.59 | 60016.7
Check | Insurance | 135.99 |  | 135.99 | 60152.69
Check | Paint Material | 45.79 |  | 45.79 | 60198.48
Check | Plumbing | 850 |  | 850 | 61048.48
Check | Painting | 4710 |  | 4710 | 65758.48
Check | Wages | 4737.34 |  | 4737.34 | 70495.82
|  | 70495.82 |  | 70495.82 | 70495.82
Actual cost report:
| Wages | 22765.05
| Permit Fee | 1958.02
| Materials | 4163.93
| Indirect Cost | 4198.82
| (S)Tile | 2500
| (S)Plumbing | 13500
| (S)Painting | 4710
| (S)Flooring | 3200
| (S)Electrical | 6000
| (S)Drywall | 7500
| ____ | 70495.82

## Comparion Report
Category | Budget | Actual Cost | P/L
Wages | 20450 | 22765.05 | -2315.05
Permit Fee | 0 | 1958.02 | -1958.02
Materials | 7776 | 4163.93 | 3612.07
Indirect Cost | 0 | 4198.82 | -4198.82
Granite Fabr. | 2600 | 0 | 2600
(S)Tile | 3500 | 2500 | 1000
(S)Plumbing | 10650 | 13500 | -2850
(S)Painting | 5710 | 4710 | 1000
(S)Flooring | 3910 | 3200 | 710
(S)Electrical | 10550 | 6000 | 4550
(S)Drywall | 10500 | 7500 | 3000
(S)Cleaning | 300 | 0 | 300
--------------------
Note: (S) means Sub Contractor
____ | ____ | ____ | 5450.18