## Comparison
PROPOSAL REQUEST FORM
[5 empty] | General Contractor |  |  | External Cost | Total
| CSI Code |  |  | Category | Material | Labor
SOFT COSTS
| 00 | 11 | 20 | Architect |  |  |  |  | 0
| 00 | 12 | 10 | Environmental Consultant |  |  |  |  | 0
| 00 | 13 | 30 | Permits and Fees |  | 0 |  |  | 0
HARD COSTS
| 01 | 01 | 40 | Final Cleaning | 50 | 250 |  |  | 300
| 02 | 41 | 05 | Demolition | 400 | 1200 |  | H | 1600
| 02 | 41 | 10 | Hauling | 600 | 600 |  | H | 1200
| 02 | 81 | 05 | Abatement |  |  |  |  | 0
| 06 | 11 | 05 | Rough Carpentry/Framing | 1700 | 4200 |  | H | 5900
| 06 | 41 | 05 | Cabinets |  | 1800 |  | H | 1800
| 06 | 61 | 05 | Countertop / Backsplash |  | 2600 |  |  | 2600
| 06 | 46 | 10 | Trim / Baseboard / Molding / Shelving | 1350 | 3400 |  | H | 4750
| 07 | 20 | 05 | Insulation | 325 | 600 |  | H | 925
| 08 | 11 | 05 | Doors & Hardware x 2 - doors | 620 | 1600 |  | H | 2220
| 08 | 50 | 10 | Window Repair | 0 | 0 |  | H | 0
| 09 | 29 | 05 | Drywall | 1500 | 8000 |  |  | 9500
| 09 | 30 | 05 | Tile |  | 3500 |  |  | 3500
| 09 | 64 | 05 | Wood Flooring (New) |  | 0 |  |  | 0
| 09 | 01 | 60 | Floor Patch / Refinish Existing | 410 | 3500 |  |  | 3910
| 09 | 91 | 05 | Painting (Interior) | 510 | 4200 |  |  | 4710
| 10 | 25 | 05 | Bath Accessories |  | 450 |  | H | 450
| 11 | 31 | 05 | Appliances |  | 250 |  | H | 250
| 12 | 20 | 05 | Window Blinds | 466 | 600 |  | H | 1066
| 22 | 10 | 05 | Rough Plumbing | 1800 | 7400 |  |  | 9200
| 22 | 10 | 10 | Tub Replacement or Glazing | 0 | 0 |  | H | 0
| 22 | 42 | 05 | Finish Plumbing Fixtures/Trim |  | 450 |  |  | 450
| 23 | 31 | 20 | Heating System |  |  |  | H | 0
| 26 | 27 | 05 | Rough Electrical | 1600 | 7500 |  |  | 9100
| 26 | 50 | 05 | Finish Electrical Fixtures / Trim |  | 450 |  |  | 450
| 28 | 23 | 05 | Low Voltage Systems (Fire/Security/Cable) | 65 | 300 |  | H | 365
| 60 | 10 | 15 | Contractor's Fee / Profit & Overhead | 250 | 250 |  | H | 500
| 90 | 20 | 15 | Construction Management Fee |  |  |  | H | 0
Subtotal GC |  |  |  |  | 11646 | 53100 |  |  | 64746
Subtotal External Cost | [7 empty] | 0 | 0
TOTAL |  |  |  |  | 11646 | 53100 |  | 0 | 64746
[5 empty] | Budget | Hours |  | Exact |  | Exact Hours | Profit
|  |  |  | WAGES | 15250 | 203.3333 | HCI Labor Cost: | 22765.05 |  | 422 | -7515.05
[7 empty] | WAGES |  | 22488.73 |  | 0
[7 empty] | WORK COMP |  | 276.32 |  | 0
|  |  |  | MATERIALS | 5776 |  |  | 4118.14 |  |  | 1657.86
|  |  |  | LUMBER OR PLIE WOOD MATERIAL |  |  | LUMBER OR PLIE WOOD MATERIAL |  | 2103.02 |  | 0
|  |  |  | Other MATERIALS |  |  | MATERIALS |  | 2015.12 |  | 0
0
|  |  |  | ELECTRICAL | 9550 |  | ELECTRICAL | 9190 |  |  | 360
0
0
|  |  |  | PLUMBING + CO#1 $5,900.00 | 15550 |  | PLUMBING | 13500 |  |  | 2050
0
|  |  |  | Tile | 3500 |  | TILING | 2500 |  |  | 1000
|  |  |  | Flooring | 3910 |  | FLOORING | 3200 |  |  | 710
|  |  |  | Countertop | 2600 |  |  | 1800 | Estimated Cost |  | 800
|  |  |  | Painting | 4710 |  | PAINTING | 4755.79 |  |  | -45.79
[7 empty] | PAINT MATERIAL |  | 45.79 |  | 0
[7 empty] | PAINTING by sub |  | 4710 |  | 0
0
|  |  |  | Drywall | 9500 |  | DRYWALL | 7500 |  |  | 2000
0
|  |  |  | Cleaning | 300 | [5 empty] | 300
0
0
0
0
|  |  |  | Building PERMIT FEE | 2664.46 |  | PERMIT FEE | 1958.02 |  |  | 706.44
|  |  |  | P&E Permit Fee | 987.37 | [5 empty] | 987.37
0
|  |  |  | Indirect Cost: |  |  | Indirect Cost: | 4198.82 |  |  | -4198.82
|  |  |  | AUTOMOBILE EXPENSE |  |  | AUTOMOBILE EXPENSE |  | 484.35 |  | 0
|  |  |  | DUES AND SUBSCRIPTIONS |  |  | DUES AND SUBSCRIPTIONS |  | 20 |  | 0
|  |  |  | GAS |  |  | GAS |  | 842.25 |  | 0
|  |  |  | GENERAL LIABILITY INSURANCE |  |  | GENERAL LIABILITY INSURANCE |  | 146.16 |  | 0
|  |  |  | HEALTH INSURANCE |  |  | HEALTH INSURANCE |  | 437.48 |  | 0
|  |  |  | HEALTH PLAN INSURANCE |  |  | HEALTH PLAN INSURANCE |  | 383.06 |  | 0
|  |  |  | INSURANCE |  |  | INSURANCE |  | 135.99 |  | 0
|  |  |  | PARKING |  |  | PARKING |  | 138.72 |  | 0
|  |  |  | PAYROLL EXPENSES MRA |  |  | PAYROLL EXPENSES MRA |  | 208.12 |  | 0
|  |  |  | PAYROLL PROCESSING FEES |  |  | PAYROLL PROCESSING FEES |  | 62 |  | 0
|  |  |  | RENT |  |  | RENT |  | 267.1 |  | 0
|  |  |  | REPAIRS & MAINTENANCE |  |  | REPAIRS & MAINTENANCE |  | 983.59 |  | 0
|  |  |  | TRANSPORTATION |  |  | TRANSPORTATION |  | 90 |  | 0
WORK COMP
[5 empty] | 74297.83 |  |  | 75485.82
[10 empty] | P&L: | -1187.99

## Cost 3.11.2022
4:26 PM
2022-03-11
Type | Account |  | Clr | Amount | Balance
Check | Wages | 1798.01 |  | 1798.01 | 1798.01
Check | Rent | 67.93 |  | 67.93 | 1865.94
Check | Transportation | 30 |  | 30 | 1895.94
Check | Permit Fee | 1958.02 |  | 1958.02 | 3853.96
Check | Plumbing | 5000 |  | 5000 | 8853.96
Check | Health Plan Insurance | 197.35 |  | 197.35 | 9051.31
Check | Plumbing | 7650 |  | 7650 | 16701.31
Check | Wages | 2396.32 |  | 2396.32 | 19097.63
Check | Lumber or plie Wood Material | 166.25 |  | 166.25 | 19263.88
Check | Materials | 138.7 |  | 138.7 | 19402.58
Check | Parking | 50 |  | 50 | 19452.58
Check | Gas | 213.25 |  | 213.25 | 19665.83
Check | Parking | 13.72 |  | 13.72 | 19679.55
Check | Payroll Processing Fees | 20 |  | 20 | 19699.55
Check | Rent | 48.49 |  | 48.49 | 19748.04
Check | Wages | 2367.12 |  | 2367.12 | 22115.16
Check | Health Plan Insurance | 30 |  | 30 | 22145.16
Check | Work Comp | 90.51 |  | 90.51 | 22235.67
Check | Health Plan Insurance | 140.71 |  | 140.71 | 22376.38
Check | Repairs & Maintenance | 331.3 |  | 331.3 | 22707.68
Check | Gas | 50 |  | 50 | 22757.68
Check | Parking | 50 |  | 50 | 22807.68
Check | Transportation | 30 |  | 30 | 22837.68
Check | Drywall | 2000 |  | 2000 | 24837.68
Check | Wages | 1404.92 |  | 1404.92 | 26242.6
Check | Gas | 149.56 |  | 149.56 | 26392.16
Check | Repairs & Maintenance | 79.11 |  | 79.11 | 26471.27
Check | Materials | 55.2 |  | 55.2 | 26526.47
Check | Work Comp | 53.94 |  | 53.94 | 26580.41
Check | Payroll Processing Fees | 15 |  | 15 | 26595.41
Check | Transportation | 30 |  | 30 | 26625.41
Check | Materials | 351.77 |  | 351.77 | 26977.18
Check | Health Plan Insurance | 15 |  | 15 | 26992.18
Check | Electrical | 6000 |  | 6000 | 32992.18
Check | Payroll Expenses MRA | 208.12 |  | 208.12 | 33200.3
Check | Rent | 150.68 |  | 150.68 | 33350.98
Check | Drywall | 5500 |  | 5500 | 38850.98
Check | Materials | 217.86 |  | 217.86 | 39068.84
Check | Health Insurance | 437.48 |  | 437.48 | 39506.32
Check | Wages | 3125.44 |  | 3125.44 | 42631.76
Check | Flooring | 3200 |  | 3200 | 45831.76
Check | General Liability Insurance | 146.16 |  | 146.16 | 45977.92
Check | Materials | 50 |  | 50 | 46027.92
Check | Tiling | 2500 |  | 2500 | 48527.92
Check | Wages | 6659.58 |  | 6659.58 | 55187.5
Check | Repairs & Maintenance | 573.18 |  | 573.18 | 55760.68
Check | Gas | 389.44 |  | 389.44 | 56150.12
Check | Parking | 10 |  | 10 | 56160.12
Check | Payroll Processing Fees | 27 |  | 27 | 56187.12
Check | Dues and Subscriptions | 20 |  | 20 | 56207.12
Check | Work Comp | 131.87 |  | 131.87 | 56338.99
Check | Lumber or plie Wood Material | 1936.77 |  | 1936.77 | 58275.76
Check | Automobile Expense | 484.35 |  | 484.35 | 58760.11
Check | Gas | 40 |  | 40 | 58800.11
Check | Parking | 15 |  | 15 | 58815.11
Check | Materials | 1201.59 |  | 1201.59 | 60016.7
Check | Insurance | 135.99 |  | 135.99 | 60152.69
Check | Paint Material | 45.79 |  | 45.79 | 60198.48
Check | Plumbing | 850 |  | 850 | 61048.48
Check | Painting | 4710 |  | 4710 | 65758.48
Check | Wages | 4737.34 |  | 4737.34 | 70495.82
|  |  |  | 70495.82 | 70495.82
| AUTOMOBILE EXPENSE | 484.35
| DRYWALL | 7500
| DUES AND SUBSCRIPTIONS | 20
| ELECTRICAL | 6000 | 3190
| FLOORING | 3200
| GAS | 842.25
| GENERAL LIABILITY INSURANCE | 146.16
| HEALTH INSURANCE | 437.48
| HEALTH PLAN INSURANCE | 383.06
| INSURANCE | 135.99
| LUMBER OR PLIE WOOD MATERIAL | 2103.02
| MATERIALS | 2015.12
| PAINT MATERIAL | 45.79
| PAINTING | 4710
| PARKING | 138.72
| PAYROLL EXPENSES MRA | 208.12
| PAYROLL PROCESSING FEES | 62
| PERMIT FEE | 1958.02
| PLUMBING | 13500
| RENT | 267.1
| REPAIRS & MAINTENANCE | 983.59
| TILING | 2500
| TRANSPORTATION | 90
| WAGES | 22488.73
| WORK COMP | 276.32